## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | OnlineBankingSystem_01
Project Name | MakeMy Journey User Reg Form
Prepared/Modified by | Role | Date of Preparation
Sree Harsha Vyas | Tester | 2018-06-27
Reviewed by | Role | Date of Review
Anudeep | SME | 2018-06-27
Approved by | Role | Date of Approval
Ganesh | Test Manager | 2018-06-27
Circulation List
Version Number | 2

## DEFECT TRACKING SHEET
Project ID: OnlineBankingSystem_01
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
BANKING_01 | Home | The application does not conatain user login module | Detailed Description: The application does not contain user login module Steps To reproduce the bug: 1. Open Browser 2. Enter following URL in the browser "http://ndafile:8081/OnlineBankingProjectSpring/" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the User Login button is miising on the home page of Application | Coding | Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-21 | Elites | xxxxx | ACT | Test Cycle 1
BANKING_02 | REGISTRATION | The Account Holder name field in the Registration page is found to accept Numbers as input. | Detailed Description: The Account Holder name field is accepting Numbers as input. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Admin Login 4.Enter Valid Admin Credentials. 5. Click on Add New Account 6. Enter Numbers in Account Holder Name Field. 7. Fill the other fields with valid details. 8. Click on Register. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the Account Holder Name field is accepting numbers as input | Coding | Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2018-07-21 | Elites | xxxxx | ACT | Test Cycle 1 | TC_MN_02
REGISTRATION_001 | REGISTRATION | The PAN card number field in registration page is found to accept all numbers | Detailed Description: The Account Holder name field is accepting Numbers as input. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Admin Login 4.Enter Valid Admin Credentials. 5. Click on Add New Account 6. Enter all the 10 characters in PAN card number field with either numbers or alphabets. 7. Fill the other fields with valid details. 8. Click on Register. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the PAN card number field is accepting both numbers and alphabets | Coding | Internet Explorer | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2018-07-21 | Elites | xxxxx | ACT | Test Cycle 1 | TC_USN_02, TC_USN_03
REGISTRATION_02 | REGISTRATION | The page is executing on clicking register even if the security question field is blank | Detailed Description: The form tends to execute on clicking register even if the security question field is left blank. To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Admin Login 4.Enter Valid Admin Credentials. 5. Click on Add New Account 6. Enter all the 10 characters in PAN card number field with either numbers or alphabets. 7. Fill the other fields with valid details. 8. Click on Register. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the registration id is not getting generated. | Coding | Internet Explorer | Internal Dev | Low | Medium | 1.1 | Build 1.0 | 2018-07-21 | Elites | xxxxx |  | Test Cycle 1 | TC_SA_02
REGISTRATION_001 | REGISTRATION | The Email id in the registration page is found to accept invalid email id's. | Detailed Description: The email id field in the registration form is accepting wrong email. Steps to reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter other Valid credentials 5.Enter inactive/wrong email for sign up. 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the email field is accepting any email id which has email format but not checking if it exists. | Coding | Internet Explorer | Internal Dev | High | Medium | 1.1 | Build 1.0 | 2018-06-27 | Sree Harsha | xxxxx |  | Test Cycle 1 | TC_EM_02